## general_report
JIRA
Displaying 132 issues at 06/Jul/15 11:27 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Epic Name | Peer Sign-off | Cascading Select | Epic Status | Epic Color | Rank | Iteration | QA Completed On | Story Points | Business Value | Total Days Spent | End Date | Sprint | Epic Link | Testing Notes status | Link to play | Frustration | [CHART] Date of First Response | Effort | Account | Incorporated Version | Flagged | Founder Sign-off | Testing Status | Epic/Theme | Morale | Team | Test Sessions | Raised During
FDA Drug Interactions | FDADI-133 | Password creation allows minimum of 4 characters | Bug | Open | Medium | Unresolved | Unassigned | Ms. Nelofur Damiani | Ms. Nelofur Damiani | 2015-06-26 14:20 | 2015-07-06 11:27 | 2015-06-26 14:28 |  | FDADI Release 1.1 | FDADI Release 1.1 |  |  | 0 | 1 | [8 empty] | The minimum number of characters for passwords should be 6, however the application allows users to create passwords with a minimum of 4 characters- register and login buttons become enabled when 4 characters are typed in the password box. | [12 empty] | 0¦i000uv: | None | [12 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-132 | Rewrite the text on the myMedication login page | Bug | Done | Medium | Fixed | Timothy Scott | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-25 12:33 | 2015-06-26 14:28 | 2015-06-25 17:09 | 2015-06-25 17:09 |  |  |  |  | 0 | 3 |  |  | 0 | 120 |  |  |  |  | Rewrite to say, "myMedications allows users to resarch information concerning the medications to include adverse reactions, drug interactions, and recalls" |  | 100% | 100% | 120 | 0 | [7 empty] | 0¦i000ub: | None |  | 1 |  |  |  | Sprint 7 |  |  |  |  | 2015-06-25 13:31 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-131 | After selecting pharm class in add medication by pharm class, the list of medications is empty. | Bug | Done | High | Fixed | Timothy Scott | Timothy Scott | Timothy Scott | 2015-06-25 12:16 | 2015-06-25 12:42 | 2015-06-25 17:09 | 2015-06-25 17:09 |  |  |  |  | 0 | 2 |  |  | 0 | 600 | [6 empty] | 100% | 100% | 600 | 0 | [7 empty] | 0¦i000u9: | None |  | 1 |  |  |  | Sprint 7 |  |  |  |  | 2015-06-25 17:09 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-130 | Need a coding style guide. It code be standard Java coding guideline. | Bug | Done | Medium | Done | William Hunt | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-25 12:16 |  | 2015-06-25 17:08 | 2015-06-25 17:08 |  |  |  |  | 0 | 1 | [21 empty] | 0¦i000u8: | None |  | 3 |  |  |  | Sprint 7 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-129 | If FAQ is selected from the log in page without logging in and when it goes to the FAQ page, there is a logout button in the corner (even though not logged in) | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-25 09:35 |  | 2015-06-25 17:09 | 2015-06-25 17:09 |  |  |  |  | 0 | 3 |  |  | 0 | 300 | [6 empty] | 100% | 100% | 300 | 0 | [7 empty] | 0¦i000uf: | None |  | 1 |  |  |  | Sprint 7 |  |  |  |  | 2015-06-25 13:27 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-128 | "Check for Drug Interactions" even though only one was selected gave an alert that medications do not interact with each other | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-25 09:30 |  | 2015-06-25 17:09 | 2015-06-25 17:09 |  |  |  |  | 0 | 2 |  |  | 0 | 120 |  |  |  |  | When I had only one medication selected in my medication list and I clicked on the "Check for Drug Interactions" button I got the message that the medications do not interact with each other, even though only one was selected. In this case the system should provide the user a message that says "please select one or more medications from your list to view drug interactions." |  | 100% | 100% | 120 | 0 | [7 empty] | 0¦i000un: | None |  | 2 |  |  |  | Sprint 7 |  |  |  |  | 2015-06-25 17:09 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-127 | If medications have drug interactions, an alert displays that there are interactions but there is no text saying what interactions there are | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 16:39 | 2015-06-29 15:06 | 2015-06-25 12:26 | 2015-06-25 12:13 |  | FDADI Release 1 |  |  | 0 | 3 | _thumb_10108.png |  | 0 | 1200 | [6 empty] | 100% | 100% | 1200 | 0 | [7 empty] | 0¦i000oi:t9 | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-25 11:12 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-126 | A medication that has no Recalls, and the recall button is selected, no content is displayed just the back button | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 16:37 |  | 2015-06-25 13:15 | 2015-06-25 08:45 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-119 | [14 empty] | 0¦i000u7: | None | [10 empty] | 2015-06-25 08:45 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-125 | Add "Select All" function in Medication List | Task | Open | Medium | Unresolved | Unassigned | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 14:33 | 2015-06-26 10:39 | 2015-06-25 13:17 | [5 empty] | 0 | 1 | [6 empty] | FDADI-59 |  | This will allow the user to multi-select all of the medications in their list at the same time, this will be helpful for users who have several medications. | [6 empty] | improvement | [5 empty] | 0¦i000tz: | None |  | 2 | [10 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-124 | Medications in the list should be formatted consistently | Task | Done | High | Won't Fix | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:14 |  | 2015-06-25 10:08 | 2015-06-25 10:08 |  | FDADI Release 1 | Front End |  | 0 | 2 | [8 empty] | When adding medications from both the pharm class and medication by name lists, the formatting of the medications is inconsistent, some medications are all upper case and some are upper and lower, the medications in the list should be in the format of upper/lower case. | [6 empty] | improvement | [5 empty] | 0¦i000oi:y | None | [10 empty] | 2015-06-25 00:43 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-123 | Alpha order the medication list when new meds are added | Task | Done | Medium | Fixed | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:09 |  | 2015-06-25 09:44 | 2015-06-25 09:44 |  | FDADI Release 1 | Front End |  | 0 | 3 | [8 empty] | When a new medication is added to the list, the new medications are not listed in alpha order, newly added medications should appear alphabetically. | [6 empty] | improvement | [5 empty] | 0¦i000oi: | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-25 00:42 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-122 | A 'Remove All' button should be added to the Medications List screen | Task | Open | Medium | Unresolved | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:07 | 2015-06-24 14:09 | 2015-06-25 13:16 |  |  | FDADI Release 1 | Front End |  | 0 | 1 | [8 empty] | On the medications list screen, there is only a manual way to remove each medication individually. Add button with functionality that will allow the user to "Remove All" of the medications in the list. The button should also be called "Remove All" | [6 empty] | improvement | [5 empty] | 0¦i000oi:v | None |  | 3 | [10 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-121 | Description on login page (see example in Description in Jira details below) | Bug | Done | Medium | Done | William Hunt | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 14:06 |  | 2015-06-25 12:27 | 2015-06-24 16:40 |  | FDADI Release 1 |  |  | 0 | 3 | [8 empty] | Example: "myMedications is an App where people can add medications to a list and find out information concerning the medications. The information included are details about the medications selected, adverse reactions, drug interactions, and recalls." | [12 empty] | 0¦i000b2:yvr | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 16:28 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-120 | clearAvenue logo should take user back to homepage when clicked | Task | Done | Medium | Done | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:04 | 2015-06-24 14:06 | 2015-06-25 09:46 | 2015-06-25 09:46 |  | FDADI Release 1 | Front End |  | 0 | 3 | [8 empty] | The clearAvenue logo is clickable, if it is to remain this way, the logo should bring the user back to the main medications list screen when it is clicked. | [6 empty] | improvement | [5 empty] | 0¦i000oi:r | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-24 20:47 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-119 | If there are no recalls on a medication a note should display to the user stating this | Task | Done | Medium | Fixed | Timothy Scott | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:02 | 2015-06-24 14:04 | 2015-06-25 08:45 | 2015-06-24 18:26 |  | FDADI Release 1 | Front End |  | 0 | 3 |  |  | 0 | 180 |  |  | FDADI-126 |  | If there are no recalls for a medication and the user goes to the recalls page, the page currently does not show any information, just a back button. Update the screen to display a note to the user that says "There are no recalls for the medication you selected." |  | 100% | 100% | 180 | 0 |  | improvement | [5 empty] | 0¦i000b2:ze | None | 2015-06-24 18:25 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 16:44 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-118 | Rename the clear button to uncheck | Task | Done | Highest | Fixed | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 14:00 | 2015-06-24 14:16 | 2015-06-24 16:39 | 2015-06-24 16:39 |  | FDADI Release 1 | Front End |  | 0 | 3 | [8 empty] | The "Clear" button should be renamed to "Uncheck," its a bit confusing for users as the term is similar to remove. | [6 empty] | improvement | [5 empty] | 0¦i000b2:yt | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 16:05 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-117 | Back button should be consistent sizing on all screens | Task | Done | High | Duplicate | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 13:57 |  | 2015-06-24 16:01 | 2015-06-24 16:01 |  | FDADI Release 1 | Front End |  | 0 | 1 | [6 empty] | FDADI-114 |  | All of the back buttons should be the same size/format on each screen, on some pages its larger and some pages its small, please make this button consistent on each screen. | [6 empty] | improvement | [5 empty] | 0¦i000oh: | None | [12 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-116 | We need to change FDADI to myMedications everywhere | Bug | Done | Medium | Fixed | William Hunt | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 13:53 |  | 2015-06-25 12:26 | 2015-06-25 09:42 |  | FDADI Release 1 |  |  | 0 | 3 | [8 empty] | We are going to export and give the government everything. Srini feels it would be better to have the wording be myMedications than FDADI for anything referring to the App (because that is what it is called now). | [12 empty] | 0¦i000oh:i | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-25 00:15 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-115 | In "Add Medication by PharmClass" if a medication is added that has multiple parts (commas and dashes) it separates them | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-24 13:29 |  | 2015-06-25 12:26 | 2015-06-25 12:11 |  | FDADI Release 1 |  |  | 0 | 3 | _thumb_10107.png |  | 0 | 2700 |  |  | FDADI-37 |  | I added a medication by PharmClass Selected Vitamin B12 Selected Get Medications for PharmClass Selected SODIUM FLUORIDE, VITAMIN A, ASCORBIC ACID, VITAMIN D, ALPHA-TOCOPHEROL, THIAMINE, RIBOFLAVIN, NIACIN, PYRIDOXINE, FOLIC ACID, AND CYANOCOBALAMIN (Tried it again with another multiple parts med - same result) When added, it did not keep the block whole, it split up the meds, and in one case even split up a med with a dash into 2 different selection in the medication list Same thing happened in "Add Medication by Name" ACETAMINOHPEN, DEXTROMETHORPHAN HBR, PHENYLEPHRINE HCL Each comma was a new selection in the medication list. |  | 100% | 100% | 2700 | 0 | [7 empty] | 0¦i000oi:ti | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-25 10:54 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-114 | Change 'Back' button to match styling guide | Bug | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-24 12:47 |  | 2015-06-25 12:27 | 2015-06-24 13:32 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-117 |  | Change button to match styling guide | [12 empty] | 0¦i000b2:yv4 | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 13:32 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-113 | Add logged in username to application title | Bug | Done | Low | Done | William Hunt | William Hunt | William Hunt | 2015-06-24 11:59 |  | 2015-06-25 12:32 | 2015-06-24 13:58 |  | FDADI Release 1 | Front End |  | 0 | 2 | [8 empty] | Add the username to the application title to indicate user is logged in | [12 empty] | 0¦i000b2:zg | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 13:58 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-112 | Failed registrations need an explanation message | Bug | Done | Medium | Fixed | Timothy Scott | William Hunt | William Hunt | 2015-06-24 11:57 |  | 2015-06-25 12:27 | 2015-06-24 12:56 |  | FDADI Release 1 |  |  | 0 | 2 |  |  | 0 | 240 |  |  |  |  | When a registration fails, there needs to be a more descriptive reason: Registration failed: Username already exists. |  | 100% | 100% | 240 | 0 | [7 empty] | 0¦i000b2:zfi | None | 2015-06-24 12:55 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 12:19 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-111 | Perform Section 508 Compliance check on website | Bug | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-24 11:56 |  | 2015-06-25 12:39 | 2015-06-24 23:56 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Perform Section 508 checking...using WAVE toolbar | [12 empty] | 0¦i000oi:u | None |  | 2 |  |  |  | Sprint 6 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-110 | Application needs a disclaimer footer on every page | Bug | Done | Medium | Fixed | Timothy Scott | Jeff Heath | Jeff Heath | 2015-06-24 11:46 |  | 2015-06-24 16:16 | 2015-06-24 15:58 | FDADI Release 1 | FDADI Release 1 | Front End |  | 0 | 3 |  |  | 0 | 1320 | [6 empty] | 100% | 100% | 1320 | 0 | [7 empty] | 0¦i000b2:zf | None | 2015-06-24 15:58 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 12:10 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-109 | Application needs an FAQ page and a link to the FAQ | Task | Open | Medium | Done | William Hunt | Jeff Heath | Jeff Heath | 2015-06-24 11:46 |  | 2015-06-25 16:07 | 2015-06-25 09:58 | FDADI Release 1 | FDADI Release 1 | Front End |  | 0 | 4 | [8 empty] | As a user, I would like to view a Frequently Asked Questions (FAQ) screen, to view the answers to some commonly asked questions. ***** - What is myMedications? myMedications is an application that allows users to create a list of drugs that are relevant to them and obtain detailed information about each specific drug including any adverse reactions that may occur, potentially harmful interactions that may occur when drugs are taken concurrently and any recalls that may have occurred. - Where does the information come from? The information is supplied by the Food and Drug Administration through the openFDA API. - Are the lists I create saved? Yes. Once a user adds a drug to the list, the list is saved and will be available to the user the next time the user logs in. - Do I need to check each category (recalls and harmful interactions) every time I login? No. The application has functionality to alert the user of any recalls and harmful interactions that may occur between medications on the list each time they login to the system. - Do I need to check for adverse reactions each time I login? Yes. Currently, myMedications does not alert a user to adverse reactions that may occur while taking medications on the user's list. We are looking at adding this functionality to a future release. | [6 empty] | improvement | [5 empty] | 0¦i000oi:t | None | [5 empty] | Sprint 6 |  |  |  |  | 2015-06-24 21:57 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-108 | Add "Forgot Password?" link on the log in page | Task | Open | Medium | Unresolved | Unassigned | Ms. Divya Sharma | Ms. Divya Sharma | 2015-06-24 11:46 | 2015-06-26 10:36 | 2015-06-25 13:17 | [5 empty] | 0 | 1 | [8 empty] | Add "Forgot Password?" link on the log in page in case a user forgets username/password. | [12 empty] | 0¦i000sf: | None |  | 3 | [10 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-107 | Language on login screen should be more descriptive for registration process | Task | Done | High | Fixed | Timothy Scott | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 11:21 |  | 2015-06-25 10:35 | 2015-06-24 12:54 |  | FDADI Release 1 | Front End |  | 0 | 3 |  |  | 0 | 120 |  |  | FDADI-85 |  | Update login screen language to reflect the following: "New Users Enter a username & password and select Register. Current Users enter your username & password and select Login" |  | 100% | 100% | 120 | 0 |  | midsprintchange | [5 empty] | 0¦i000b2:zd | None | 2015-06-24 12:54 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 12:02 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-106 | Warning Message displays for recalls with no medications in the list | Bug | Done | Medium | Cannot Reproduce | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-24 07:21 | 2015-06-24 11:54 | 2015-06-24 18:12 | 2015-06-24 16:10 |  | FDADI Release 1 | Front End |  | 0 | 2 | [8 empty] | Upon logging in with my UN and PW, the "Warning Message" is displayed stating "Warning: The following medications have ongoing recalls:" but I do not have any medications in my list. This happened after I used the remove button to remove medications from the list and logged out and logged back in with my credentials. I created a new UN and PW and clicked Register and this did not happen. | [12 empty] | 0¦i000oj: | None | [10 empty] | 2015-06-24 16:10 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-105 | update Technical Document | Task | Done | Medium | Done | Gopal Kankanahalli | Gopal Kankanahalli | Gopal Kankanahalli | 2015-06-24 06:26 |  | 2015-06-25 10:35 | 2015-06-24 18:24 |  | FDADI Release 1 |  |  | 0 | 1 | [21 empty] | 0¦i000rz: | None | [5 empty] | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-104 | Update application styling | Bug | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-24 00:32 |  | 2015-06-25 12:27 | 2015-06-24 12:27 |  | FDADI Release 1 |  |  | 0 | 1 | [21 empty] | 0¦i000b2:z9 | None | 2015-06-24 12:00 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-103 | Standardize button styling | Bug | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-24 00:15 |  | 2015-06-25 12:28 | 2015-06-24 11:57 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create buttons to have a consistent, smaller style | [12 empty] | 0¦i000b2:yvi | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 11:57 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-102 | sometimes medicine details returns drug interactions. Need additional testing | Bug | Done | Medium | Won't Do | William Hunt | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:30 |  | 2015-06-25 13:15 | 2015-06-23 22:51 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000rr: | None | [10 empty] | 2015-06-23 22:51 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-101 | if a medication is selected and upon pressing clear, the medication is not cleared | Bug | Done | Medium | Cannot Reproduce | Timothy Scott | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:27 |  | 2015-06-25 13:16 | 2015-06-25 09:54 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000rj: | None | [10 empty] | 2015-06-23 22:53 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-100 | Adverse reactions has too much text. Is there a way to only show the adverse reactions? | Task | Done | Medium | Won't Fix | William Hunt | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:26 |  | 2015-06-25 14:00 | 2015-06-25 09:53 |  | FDADI Release 1 |  |  | 0 | 2 | [15 empty] | improvement | [5 empty] | 0¦i000rb: | None | [10 empty] | 2015-06-23 22:47 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-99 | For the drug interactions, if there is no interaction with a drug the drug still appears with nothing in the description. The drug header should not appear | Bug | Done | Medium | Fixed | Timothy Scott | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:24 |  | 2015-06-25 12:27 | 2015-06-24 12:24 |  | FDADI Release 1 |  |  | 0 | 3 | _thumb_10106.png |  | 0 | 1200 | [6 empty] | 100% | 100% | 1200 | 0 | [7 empty] | 0¦i000b2:yv9 | None | 2015-06-24 12:22 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 00:31 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-98 | The Get Medications is confusing when we add medication by pharma class | Task | Done | Medium | Won't Do | William Hunt | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:21 |  | 2015-06-25 14:00 | 2015-06-25 00:44 |  | FDADI Release 1 |  |  | 0 | 2 | [15 empty] | improvement | [5 empty] | 0¦i000qv: | None | [10 empty] | 2015-06-25 00:44 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-97 | The clearAvenue logo needs to be smaller | Bug | Done | Medium | Fixed | William Hunt | Srinivas Kankanahalli [Administrator] | Srinivas Kankanahalli [Administrator] | 2015-06-23 20:21 |  | 2015-06-25 12:29 | 2015-06-24 09:48 |  | FDADI Release 1 | Front End |  | 0 | 2 | [6 empty] | FDADI-79 | [14 empty] | 0¦i000b2:yx | None | [5 empty] | Sprint 5 | FDA Drug Interactions |  |  |  | 2015-06-24 09:48 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-96 | As a user, I want to remove medications from my Medications List so I may view only relevant medications. | Story | Done | High | Done | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-23 19:52 |  | 2015-06-24 15:59 | 2015-06-24 09:49 |  | FDADI Release 1 | Front End |  | 0 | 3 | [8 empty] | As a user, I want to remove medications from my Medications List so I may view only relevant medications. Acceptance Criteria: 1. User must be able to view all the medications in the Medications List --System displays all previously added medications in the Medication List 2 User must be able to view the 'Remove Medications' button on the Medications List page --System displays the 'Remove Medications' button to the user 3. User must be able to select the medications in the 'Medications List' they no longer wish to view --System highlights the selected medications --User selects medications no longer desired on the Medications List and 4. User must be able to select the 'Remove Medications' button --User select the 'Remove Medications' button and previously selected medications are removed from the 'Medications List' | [12 empty] | 0¦i000b2:yw | None |  | 3 |  |  |  | Sprint 5 |  |  |  |  | 2015-06-23 23:23 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-95 | Nothing displayed when selecting multiple check boxes in get medication by pharmClass | Bug | Done | Medium | Cannot Reproduce | Timothy Scott | Mr. Gregory Noyes | Mr. Gregory Noyes | 2015-06-23 16:14 |  | 2015-06-25 14:00 | 2015-06-24 07:18 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-37 |  | When a user selects add medication by pharmclass on the main profile page the user is sent to page that holds all of the pharmacy classes. When multiple selections are made on this page and "get medications" is clicked, user is taken to the add medication page with no medications displayed in the list. (If only 1 item is selected there is no issue) | [12 empty] | 0¦i000q7: | None | [6 empty] | FDA Drug Interactions |  |  |  | 2015-06-24 00:28 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-94 | FDADI-18 Story View | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-23 15:37 |  | 2015-06-25 10:56 | 2015-06-23 16:50 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000pz: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 16:50 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-93 | Display details page displays wrong medication | Bug | Done | Medium | Fixed | William Hunt | Timothy Scott | Timothy Scott | 2015-06-23 14:28 |  | 2015-06-25 12:30 | 2015-06-23 15:31 |  | FDADI Release 1 |  |  | 0 | 2 |  |  | 0 | 600 |  |  | FDADI-45 |  | Display page shows information about wrong medication |  | 100% | 100% | 600 | 0 | [7 empty] | 0¦i000pr: | None | [5 empty] | Sprint 4 | FDA Drug Interactions |  |  |  | 2015-06-23 15:31 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-92 | Change buttons on login page to look better | Bug | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-23 12:46 |  | 2015-06-25 12:30 | 2015-06-23 14:25 |  | FDADI Release 1 | Front End |  | 0 | 2 |  |  | 0 | 1800 |  |  |  |  | Change the login and register buttons to be horizontal instead of vertical. |  | 100% | 100% | 1800 | 0 | [7 empty] | 0¦i000b2:x2 | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 14:25 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-91 | Unable to Clear Medications from List | Bug | Done | Medium | Won't Do | William Hunt | Ms. Christina Paleczka | Ms. Christina Paleczka | 2015-06-23 11:50 |  | 2015-06-24 18:09 | 2015-06-23 12:42 |  | FDADI Release 1 | Front End |  | 0 | 2 | [6 empty] | FDADI-26 |  | When selecting the 'clear' button in the medications list, medications do not clear, rather they persist in the system. Please see attached screen shot. | [12 empty] | 0¦i000pj: | None | [10 empty] | 2015-06-23 12:42 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-90 | Login alert warning contains extra comma at end of string | Bug | Done | Medium | Fixed | Timothy Scott | William Hunt | William Hunt | 2015-06-23 11:41 |  | 2015-06-25 12:31 | 2015-06-23 12:24 |  | FDADI Release 1 | Front End |  | 0 | 1 | _thumb_10105.png | [5 empty] | FDADI-18 |  | Login alert warning contains extra comma at end of string... For instance: WARNING: The following medications are recalled: Advil, Ibuprofen, | [12 empty] | 0¦i000b2:x4 | None | 2015-06-23 12:24 |  |  |  |  | Sprint 4 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-89 | Clicking Medication Details link when nothing is selected errors | Bug | Done | Medium | Fixed | Timothy Scott | William Hunt | William Hunt | 2015-06-23 11:29 |  | 2015-06-25 12:31 | 2015-06-23 12:25 |  | FDADI Release 1 | Front End |  | 0 | 1 | [6 empty] | FDADI-53 |  | Clicking medication details button errors when no medications are selected | [12 empty] | 0¦i000b2:x9 | None | 2015-06-23 12:24 |  |  |  |  | Sprint 4 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-88 | Every medication added is showing as recalled | Bug | Done | Medium | Won't Do | Timothy Scott | William Hunt | William Hunt | 2015-06-23 11:29 |  | 2015-06-25 12:31 | 2015-06-23 11:38 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-19, FDADI-18 |  | Every medicine added is saying recalled even though it is not on the recall list at api.fda.gov/drug/enforcement | [12 empty] | 0¦i000b2:xi | None | [5 empty] | Sprint 4 | FDA Drug Interactions |  |  |  | 2015-06-23 11:38 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-87 | Registering a new user with the same name as an existing user allows you to log in as that user. | Bug | Done | Medium | Fixed | William Hunt | Timothy Scott | Timothy Scott | 2015-06-23 11:13 |  | 2015-06-25 12:30 | 2015-06-23 15:12 |  | FDADI Release 1 |  |  | 0 | 2 |  |  | 0 | 900 | [6 empty] | 100% | 100% | 900 | 0 | [7 empty] | 0¦i000b2:x1i | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 15:07 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-86 | Create way for user to accept warning notification/alert/dialog and have it not alert again or choose to not accept it and have it alert again | Bug | Done | Medium | Won't Fix | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 11:00 |  | 2015-06-25 12:31 | 2015-06-23 14:06 |  | FDADI Release 1 |  |  | 0 | 2 |  |  | 0 | 900 |  |  | FDADI-34 |  |  |  | 100% | 100% | 900 | 0 | [7 empty] | 0¦i000p3: | None | [10 empty] | 2015-06-23 13:58 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-85 | Create descriptive subtitle/paragraph on log in page | Task | Done | Medium | Done | William Hunt | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 10:21 |  | 2015-06-25 10:35 | 2015-06-24 12:26 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-21, FDADI-107 |  | So that users understand what site is used for (new users won't know what FDADI means nor its purpose.) | [6 empty] | midsprintchange | [5 empty] | 0¦i000b2:yy | None | 2015-06-24 12:00 |  |  |  |  | Sprint 5 |  |  |  |  | 2015-06-24 12:26 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-84 | Create search function in "Add Medication by Name" | Task | Open | Medium | Unresolved | Unassigned | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 09:17 |  | 2015-06-25 13:17 | [5 empty] | 0 | 1 | [6 empty] | FDADI-69 | [14 empty] | 0¦i000on: | None |  | 5 | [10 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-83 | Unable to register | Bug | Done | Medium | Cannot Reproduce | Timothy Scott | Ms. Divya Sharma | Ms. Divya Sharma | 2015-06-23 09:12 |  | 2015-06-25 12:31 | 2015-06-23 13:43 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Unable to register on the Login page. | [12 empty] | 0¦i000of: | None | [10 empty] | 2015-06-23 11:11 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-81 | Create method to go back a page or to home page | Bug | Done | Medium | Fixed | Timothy Scott | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 09:00 |  | 2015-06-25 12:30 | 2015-06-23 14:25 |  | FDADI Release 1 |  |  | 0 | 3 |  |  | 0 | 3600 | [6 empty] | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000b2:yr | None | 2015-06-23 14:25 |  |  |  |  | Sprint 4 |  |  |  |  | 2015-06-23 13:08 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-80 | Create method to log out | Bug | Done | Medium | Done | William Hunt | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 08:59 |  | 2015-06-25 12:29 | 2015-06-24 10:11 |  | FDADI Release 1 |  |  | 0 | 3 | [21 empty] | 0¦i000b2:yv | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-23 22:25 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-79 | Add clearAvenue logo on every page | Bug | Done | Medium | Done | William Hunt | Ms. Jenny Katz | Ms. Jenny Katz | 2015-06-23 08:57 |  | 2015-06-25 12:30 | 2015-06-23 16:52 |  | FDADI Release 1 |  |  | 0 | 3 |  |  | 0 | 1500 |  |  | FDADI-97 |  |  |  | 100% | 100% | 1500 | 0 | [7 empty] | 0¦i000b2:x19 | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 16:08 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-78 | Issue when adding multiple medications at the same time | Bug | Done | High | Fixed | Timothy Scott | Mr. Gregory Noyes | Mr. Gregory Noyes | 2015-06-23 07:49 |  | 2015-06-25 12:26 | 2015-06-23 14:18 |  | FDADI Release 1 | Front End |  | 0 | 3 | _thumb_10103.png |  | 0 | 900 |  |  |  |  | When adding medications, if user selects multiple medications at the same time, all medications are added under one block instead of in a separate block for each medication added. Each medication should be separated so each will have their own check box for modification purposes. Alternate solution: Allow users to select only one medication at a time. Screenshot added for clarity. |  | 100% | 100% | 900 | 0 | [7 empty] | 0¦i000b2:x1 | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 13:40 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-77 | User unable to register a new username and password | Bug | Done | Medium | Fixed | William Hunt | Ms. Nelofur Damiani | Ms. Nelofur Damiani | 2015-06-22 19:20 | 2015-06-22 21:05 | 2015-06-25 12:30 | 2015-06-22 19:46 |  | FDADI Release 1 | Front End |  | 0 | 2 | [6 empty] | FDADI-24 |  | The system displays the log in page. User selects register. The system does not react and the user cannot register a log in name/ password | [12 empty] | 0¦i000b2:y9 | None | 2015-06-22 19:46 |  |  |  |  | Sprint 4 |  |  |  |  | 2015-06-22 19:24 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-76 | All medication test incorrect | Bug | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-22 18:48 | 2015-06-22 19:16 | 2015-06-25 12:31 | 2015-06-22 18:57 |  | FDADI Release 1 | Database |  | 0 | 1 | [8 empty] | Updated with real medications but did not update the strings in the test | [12 empty] | 0¦i000b2:t | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-75 | Incorrect version of org.json | Bug | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-19 23:13 |  | 2015-06-25 12:31 | 2015-06-19 23:21 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 60 |  |  |  |  | Need to change the version in the pom.xml for org.json from 20141113 to the older version 20140107 |  | 100% | 100% | 60 | 0 | [7 empty] | 0¦i000b2:o | None | 2015-06-19 23:21 |  |  |  |  | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-74 | Fix FindBugs failures | Bug | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-19 17:23 |  | 2015-06-25 12:31 | 2015-06-19 17:30 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 1200 |  |  |  | Local | Correct findbug issues |  | 100% | 100% | 1200 | 0 | [7 empty] | 0¦i000b2:m | None | [5 empty] | Sprint 2 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-73 | FDADI-23 Test Case R1.1 | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-19 17:15 |  | 2015-06-25 11:07 | 2015-06-19 22:53 |  | FDADI Release 1 | Front End |  | 0 | 1 |  |  | 0 | 7200 |  |  |  |  | Test Case R1.1 Precondition: User already registered Postcondition: User logged in and title contains "FDADI - _userId_" |  | 100% | 100% | 7200 | 0 | [7 empty] | 0¦i000eb: | None | [5 empty] | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-72 | FDADI-23 Story Review | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-19 17:08 | 2015-06-22 21:19 | 2015-06-25 11:07 | 2015-06-20 18:02 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000n3: | None | [5 empty] | Sprint 2 |  |  |  |  | 2015-06-20 18:02 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-71 | FDADI-20 Story Review | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-19 17:07 |  | 2015-06-25 11:07 | 2015-06-20 18:01 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000mv: | None | [5 empty] | Sprint 2 |  |  |  |  | 2015-06-20 18:01 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-70 | FDADI-26 Create Method to Delete Medication | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-19 09:48 |  | 2015-06-25 11:07 | 2015-06-20 21:46 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 7200 |  |  |  |  | Create a method that will delete a medication from the user profile |  | 100% | 100% | 7200 | 0 | [7 empty] | 0¦i000f9: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-69 | FDADI-26 Create Method to Add User Medication | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-19 09:48 |  | 2015-06-25 10:59 | 2015-06-20 21:45 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 7200 |  |  | FDADI-84 |  | Create the method that will add a medication to the user profile |  | 100% | 100% | 7200 | 0 | [7 empty] | 0¦i000f7: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-68 | FDADI-64 Story Review | Sub-task | Done | Medium | Done | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:58 |  | 2015-06-25 10:55 | 2015-06-24 14:45 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000mn: | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-23 16:49 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-67 | FDADI-64 Recall Medication List Manual Test Case 1 | Sub-task | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-18 14:57 |  | 2015-06-25 10:56 | 2015-06-24 12:53 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Manual Test Case 1 # Login as valid user # Select a medication on the users medication list # Click the 'Recalls' button # Verify that the page displays either 'No Results' if there are no recalls, or the contents of the recall for the selected medication | [12 empty] | 0¦i000mf: | None | 2015-06-24 12:53 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-66 | FDADI-64 Create Recall Status Page | Sub-task | Done | Medium | Fixed | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:57 |  | 2015-06-25 10:56 | 2015-06-24 12:50 |  | FDADI Release 1 |  |  | 0 | 1 | [6 empty] | FDADI-65 |  | Create a page that displays the recall status for each selected medication | [12 empty] | 0¦i000m7: | None | 2015-06-24 12:50 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-65 | FDADI-64 Create UI Element to Display Recall Status | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:57 |  | 2015-06-25 10:56 | 2015-06-24 12:51 |  | FDADI Release 1 |  |  | 0 | 1 | [6 empty] | FDADI-66 |  | Create a ‘Display Recall Status’ button on the main screen | [12 empty] | 0¦i000lz: | None | 2015-06-24 12:51 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-64 | As a user, I want to select one or more medications from my medication list and have the system display a list of all active medication recalls for the selected medications | Story | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:56 |  | 2015-06-24 15:09 | 2015-06-24 14:46 |  | FDADI Release 1 |  |  | 0 | 3 |  |  | 0 | 1800 |  | FDADI-65, FDADI-66, FDADI-67, FDADI-68 |  |  | As a user, I want to select one or more medications from my medication list and have the system display a list of all active medication recalls for the selected medications. Acceptance Criteria: 1. User must be able to view the "Recalls" button --System will display the "Recalls" button on the Medications List screen 2. User must be able to multi-select medications from the medications list and click the "Recalls" button --System will allow the user to click the "Recalls" button and recalls for the medication are displayed (Exception - If no recalls are know for the selected medication(s) the system will display the following notice to the user "There are no recalls for the medication you selected." |  | 100% | 100% | 1800 | 0 | [7 empty] | 0¦i000b2:zi | None |  | 3 |  |  |  | Sprint 5 | FDA Drug Interactions |  |  |  | 2015-06-23 16:10 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-63 | FDADI-59 Story Review | Sub-task | Done | Medium | Done | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:55 |  | 2015-06-25 10:55 | 2015-06-24 14:45 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000lr: | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-23 16:48 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-62 | FDADI-59 Check Drug Interactions Manual Test Case 1 | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:55 |  | 2015-06-25 10:55 | 2015-06-24 14:44 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Manual Test Case 1 # Login as valid user # Select 2 medications from the users medication list that have drug interactions # Click the 'Check Drug Interactions' button # Verify that an alert box is displayed indicating if there is a drug interaction | [12 empty] | 0¦i000lj: | None | 2015-06-24 14:44 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-61 | FDADI-59 Create Drug Interactions Page | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:55 |  | 2015-06-25 10:55 | 2015-06-24 14:44 |  | FDADI Release 1 |  |  | 0 | 1 | [6 empty] | FDADI-60 |  | Create a page that displays drug interactions between the medications selected by the user | [12 empty] | 0¦i000lb: | None | 2015-06-24 14:44 |  |  |  |  | Sprint 5 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-60 | FDADI-59 Create a UI Element to Display Drug Interactions | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:55 |  | 2015-06-25 10:55 | 2015-06-24 13:35 |  | FDADI Release 1 |  |  | 0 | 2 | [6 empty] | FDADI-61 |  | Create a ‘Display Drug Interactions’ button on the main screen | [12 empty] | 0¦i000l3: | None | [5 empty] | Sprint 5 |  |  |  |  | 2015-06-24 13:35 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-59 | As a user, I want to select one or more medications from my medication list, and have the system display a list of drug interactions between the selected items so I can view potential interactions. | Story | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:54 |  | 2015-06-24 16:50 | 2015-06-24 14:45 |  | FDADI Release 1 | Front End |  | 0 | 2 |  |  | 0 | 1620 |  | FDADI-60, FDADI-61, FDADI-62, FDADI-63 | FDADI-125 |  | As a user, I want to select one or more medications from my medication list, and have the system display a list of drug interactions between the selected items so I can view potential interactions. Acceptance Criteria: 1. User must be able to view the 'Check for Drug Interactions' button --The system will display the 'Check for Drug Interactions' button on the Medications List screen 2. User must be able to select the 'Check for Drug Interactions' button --When user selects the 'Check for Drug Interactions' button the system will display a message that states "The selected medications do not interact with each other." (Exception - If there are interactions a message will be displayed that the selected medications have interactions) |  | 100% | 100% | 1620 | 0 | [7 empty] | 0¦i000b2:z | None | 2015-06-24 14:45 | 8 |  |  |  | Sprint 5 | FDA Drug Interactions |  |  |  | 2015-06-23 15:41 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-58 | FDADI-53 Story Review | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:53 |  | 2015-06-25 10:56 | 2015-06-23 16:47 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000kv: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 16:47 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-57 | FDADI-53 Display Adverse Effects Test Case 1 | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:53 |  | 2015-06-25 10:56 | 2015-06-23 15:36 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Manual Test # Login with valid user # Select a medication from user medication list # Click the 'Show Adverse Effects' button # Verify only adverse effects for selected medication is shown | [12 empty] | 0¦i000kn: | None | [5 empty] | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-56 | FDADI-53 Create Adverse Effects page | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:53 |  | 2015-06-25 10:57 | 2015-06-23 15:30 |  | FDADI Release 1 |  |  | 0 | 2 |  |  | 0 | 3600 |  |  |  |  | Create a page that displays the Adverse Effects for each medication selected |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000kf: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 13:08 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-55 | FDADI-53 Add ability to select one or more medications in the medication list | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:52 |  | 2015-06-25 10:58 | 2015-06-23 11:43 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Add ability to select one or more medications in the medication list | [12 empty] | 0¦i000k7: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 11:43 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-54 | FDADI-53 Create UI Element to Show Adverse Effects | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:52 |  | 2015-06-25 10:59 | 2015-06-23 10:24 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create a ‘Show Adverse Effects’ button on the main screen | [12 empty] | 0¦i000jz: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 10:24 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-53 | Display adverse effects for selected medications | Story | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:51 |  | 2015-06-24 15:39 | 2015-06-23 15:38 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-54, FDADI-55, FDADI-56, FDADI-57, FDADI-58 | FDADI-89 |  | As a user, I want to select one or more medications from my medication list and display a list of adverse effects for each medication selected on a new page so that I can choose to take it or not. |  |  | 100% | 3600 | 0 | [7 empty] | 0¦i000b2:y | None |  | 5 |  |  |  | Sprint 4 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-52 | FDADI-45 Story Review | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:50 |  | 2015-06-25 10:56 | 2015-06-23 16:46 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000jr: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 16:46 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-51 | FDADI-45 Show Detail page Test Case 1 | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:49 |  | 2015-06-25 10:56 | 2015-06-23 15:34 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Manual Test: # Login with valid user # Select a medication from user medication list # Click the Show Details button # Verify the details are for the selected medication | [12 empty] | 0¦i000jj: | None | 2015-06-23 15:34 |  |  |  |  | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-50 | FDADI-45 Create a page that display the medication details | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:49 |  | 2015-06-25 10:58 | 2015-06-23 12:28 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create a page that displays the medication details. The details should include: adverse effects, medication usage, drug interactions, and counteractions | [12 empty] | 0¦i000jb: | None | 2015-06-23 12:27 |  |  |  |  | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-49 | FDADI-45 Create a method that takes a JSON string and extract the contraindications | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:49 |  | 2015-06-25 10:58 | 2015-06-23 11:04 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 1800 |  |  |  |  | Create a method that takes a JSON string and extract the contraindications |  | 100% | 100% | 1800 | 0 | [7 empty] | 0¦i000j3: | None | [5 empty] | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-48 | FDADI-45 Create a method that takes a JSON string and extract the medication usage | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:49 |  | 2015-06-25 10:58 | 2015-06-23 11:04 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 1800 |  |  |  |  | Create a method that takes a JSON string and extract the medication usage |  | 100% | 100% | 1800 | 0 | [7 empty] | 0¦i000iv: | None | [5 empty] | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-47 | FDADI-45 Create a method that takes a JSON string and extract the Adverse Effects | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:48 |  | 2015-06-25 10:58 | 2015-06-23 11:04 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 1800 |  |  |  |  | Create a method that takes a JSON string and extract the Adverse Effects |  | 100% | 100% | 1800 | 0 | [7 empty] | 0¦i000in: | None | [5 empty] | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-46 | FDADI-45 Add ability to select or clear medications in the medication list | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:48 |  | 2015-06-25 10:59 | 2015-06-23 09:49 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Add ability to select and clear medication(s) in the medication list | [12 empty] | 0¦i000if: | None | [5 empty] | Sprint 4 |  |  |  |  | 2015-06-23 09:49 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-45 | As a user, I want the ability to view a Details page option for any medication in my medication list so I can view adverse effects, medication usage, drug interactions, and counteractions. | Story | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:48 | 2015-06-22 19:03 | 2015-06-24 15:39 | 2015-06-23 17:12 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-46, FDADI-47, FDADI-48, FDADI-49, FDADI-50, FDADI-51, FDADI-52 | FDADI-93 |  | As a user, I want the ability to view a Details page option for any medication in my medication list so I can view adverse effects, medication usage, drug interactions, and counteractions. Acceptance Criteria: 1. User must be able to add a medication to the Medication List by Name and PharmClass -- User clicks the 'Add Medication by Name' button or the 'Add Medication by PharmClass' button to add desired medication from the system generated list 2. User must be able to select the checkbox next to the medication -- User selects the checkbox next to the medication(s) and the system highlights the medication in blue 3. User must be able to click the 'Medicine Details' button to view usage and usage indication information -- User clicks the 'Medicine Details' button and the system displays a details page with usage and usage indications information 4. User must be able to click the 'Adverse Reactions' button to view adverse affects/reactions for the selected medication(s) -- User clicks the 'Adverse Reactions' button and the system displays a page that details the medication warnings and adverse reactions |  |  | 100% | 5400 | 0 | [7 empty] | 0¦i000b2:x | None |  | 8 |  |  |  | Sprint 4 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-44 | FDADI-37 Story Review | Sub-task | Done | Medium | Won't Do | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:47 |  | 2015-06-25 10:59 | 2015-06-22 18:17 |  | FDADI Release 1 |  |  | 0 | 1 | [21 empty] | 0¦i000i7: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-43 | FDADI-37 Test Case 1 | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:47 |  | 2015-06-25 11:00 | 2015-06-22 18:16 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Manual test # Login with valid user # Click the Add By Pharmaceutical Class button # Select a class and click 'Get Medicines' # Select a medicine and click 'Add Medicine' # Verify the new medicine is in the medication List | [12 empty] | 0¦i000hz: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-42 | FDADI-37 Display Pharmaceutical Class List and Associated Medication List on the Dialog | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:46 |  | 2015-06-25 11:00 | 2015-06-22 18:10 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create a dialog screen to display the pharmaceutical class list and upon selecting one, display the corresponding medication list | [12 empty] | 0¦i000hr: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-41 | FDADI-37 Create Method to Query the Label API by Pharmaceutical Class | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:45 |  | 2015-06-25 11:06 | 2015-06-22 18:06 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create a method to query the Label API by pharmaceutical class and return a list of medicine names | [12 empty] | 0¦i000hj: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-40 | FDADI-37 Create Method to Query for Pharmaceutical Class in MongoDB | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:44 |  | 2015-06-25 11:06 | 2015-06-20 23:55 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Create a method to query the pharmaceutical class collection in the MongoDB and return a list of pharmaceutical classes |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000hb: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-39 | FDADI-37 Add Pharmaceutical Class Collection in MongoDB | Sub-task | Done | Medium | Incomplete | William Hunt | William Hunt | William Hunt | 2015-06-18 14:43 |  | 2015-06-25 11:06 | 2015-06-20 23:54 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Create a pharmaceutical class collection in the MongoDB |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000h3: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-38 | FDADI-37 Create Method to Add by Pharmaceutical Class Element | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:43 |  | 2015-06-25 11:01 | 2015-06-22 18:10 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create an ‘Add by Pharmaceutical Class’ button on the main screen | [12 empty] | 0¦i000gv: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-37 | As a user, I want to add a medication by pharmaceutical class to find my medication easily. | Story | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:41 | 2015-06-23 18:03 | 2015-06-25 14:01 | 2015-06-22 18:17 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-38, FDADI-39, FDADI-40, FDADI-41, FDADI-42, FDADI-43, FDADI-44 | FDADI-95, FDADI-115 |  | As a user, I want to add a drug by pharmaceutical class and be alerted to any recalls or drug interactions between my existing medications through a prompt that asks me if I want to "add" or "reject" the medication. Acceptance Criteria: 1.User selects "Add Medication by Pharm Class" --System displays "All Pharmaceutical Class List" 2. User single selects from the Class List and selects "Get Medication" --System displays list filtered by user selection. (Exception) User can select clear to remove the selection (Exception) User can select cancel to navigate back to main search page. |  |  | 100% | 7200 | 0 | [7 empty] | 0¦i000b2:v | None |  | 5 |  |  |  | Sprint 3 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-36 | FDADI-26 Story Review | Sub-task | Done | Medium | Won't Do | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:38 |  | 2015-06-25 10:59 | 2015-06-22 18:17 |  | FDADI Release 1 |  |  | 0 | 1 | [21 empty] | 0¦i000gn: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-35 | FDADI-26 Login Test Cases | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:38 |  | 2015-06-25 11:07 | 2015-06-22 10:24 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create an automatic test that will perform the following tests for the login page. Test Case 1 - Verify redirected to login if you are not logged in 1) Navigate to index page 2) Verify redirected to login page and the title of the page is 'FDADI Login' Test Case 2 - Verify logging in with valid user/pwd goes to index page 1) Navigate to index page 2) Login with valid user/pwd 3) Verify title of page is 'FDADI - username' Test Case 3 - Verify logging in with invalid user/pwd goes to index page 1) Navigate to index page 2) Login with valid user but invalid password 3) Verify URL contains 'loginError' | [12 empty] | 0¦i000gf: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-34 | FDADI-26 Create Dialog to Alert Medication Interactions or Recalls | Sub-task | Done | Medium | Incomplete | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:38 |  | 2015-06-25 10:59 | 2015-06-22 18:52 |  | FDADI Release 1 |  |  | 0 | 1 | [6 empty] | FDADI-86 |  | Create a dialog screen to allow the acceptance or rejection of adding a drug to the medication list if a recall or drug interaction is found | [12 empty] | 0¦i000g7: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-33 | FDADI-26 Create Method to Determine Medication Interactions | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:37 |  | 2015-06-25 11:07 | 2015-06-22 10:20 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create a method that queries a list of multiple medications and their corresponding drug interactions to return a list of medication pairs that interact with each other | [12 empty] | 0¦i000fz: | None | [5 empty] | Sprint 3 |  |  |  |  | 2015-06-22 10:20 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-32 | FDADI-26 Create Method to Extract Drug Interactions | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:36 |  | 2015-06-25 11:07 | 2015-06-22 10:20 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create a method that takes a JSON string and extracts the Drug Interactions | [12 empty] | 0¦i000fr: | None | [5 empty] | Sprint 3 |  |  |  |  | 2015-06-22 10:20 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-31 | FDADI-26 Create Method to Query Label Information | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:35 |  | 2015-06-25 11:08 | 2015-06-19 12:39 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create a method to query the Label API using a given medication name and return a JSON string representing the medication info | [12 empty] | 0¦i000fj: | None | [5 empty] | Sprint 3 |  |  |  |  | 2015-06-19 12:39 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-30 | FDADI-26 Create Method to Query Recall Status | Sub-task | Done | Medium | Done | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:34 |  | 2015-06-25 11:08 | 2015-06-19 12:38 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create a method to query the Enforcement reports API using a given medication name to return an object that represents a medication is currently listed as part of an ongoing recall status. | [12 empty] | 0¦i000fb: | None | [5 empty] | Sprint 3 |  |  |  |  | 2015-06-19 12:38 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-29 | FDADI-26 Create Method to Retrieve Medication Names | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:33 |  | 2015-06-25 11:07 | 2015-06-20 22:34 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Create a method to query the medication name collection in the MongoDB and return a list of medication names |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000f3: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-28 | FDADI-26 Add Collection of Medication Names in MongoDB | Sub-task | Done | Medium | Incomplete | William Hunt | William Hunt | William Hunt | 2015-06-18 14:32 |  | 2015-06-25 11:07 | 2015-06-20 22:33 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Create a medication name collection in the MongoDB |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000ev: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-27 | FDADI-26 Update Main Screen | Sub-task | Done | Medium | Incomplete | William Hunt | William Hunt | William Hunt | 2015-06-18 14:31 |  | 2015-06-25 11:07 | 2015-06-21 19:29 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 10800 |  |  |  |  | Create an ‘Add by Medication Name’ button on the main screen |  | 100% | 100% | 10800 | 0 | [7 empty] | 0¦i000en: | None | [5 empty] | Sprint 3 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-26 | As a user, I want to add a drug by name to my medication list so I can find the medication easily. | Story | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:29 | 2015-06-23 17:53 | 2015-06-25 15:59 | 2015-06-22 18:58 |  | FDADI Release 1 |  |  | 0 | 2 | [5 empty] | FDADI-27, FDADI-28, FDADI-29, FDADI-30, FDADI-31, FDADI-32, FDADI-33, FDADI-34, FDADI-35, FDADI-36, FDADI-69, FDADI-70 | FDADI-91 |  | As a user, I want to add a drug by name to my medication list, and be alerted through a prompt to add or reject any drug that has a recall or carries interactions between my existing medications. Acceptance Criteria: 1.User selects "Add Medication by Name" -- System displays a list of medications by name 2.User multi selects the medication to filter list. (Exception) User can select "clear" to remove selections 3. User selects "Add Medication" -- System displays list of selected medications 4. User can multi select from the filter listed and select "clear" to remove selections. (Exception) User can select "cancel" to navigate to main search page. |  |  | 100% | 32400 | 0 | [7 empty] | 0¦i000b2:r | None |  | 8 |  |  |  | Sprint 3 | FDA Drug Interactions |  |  |  | 2015-06-25 15:59 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-25 | FDADI-23 Create Login Validation Method | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:28 |  | 2015-06-25 11:08 | 2015-06-19 20:45 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Devise a method to validate the user credentials against their stored profile by: 1. Ensuring password encryption and verification logic 2. Validating encryption before saving | [12 empty] | 0¦i000ef: | None | [5 empty] | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-24 | FDADI-23 Create Login Screen | Sub-task | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-18 14:28 | 2015-06-22 19:09 | 2015-06-25 10:59 | 2015-06-19 22:53 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 7200 |  |  | FDADI-77 |  | Create the login screen for user to access and gain entry into the application |  | 100% | 100% | 7200 | 0 | [7 empty] | 0¦i000e7: | None | [5 empty] | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-23 | As a user, I need to have the ability to view login dialog so I know if I have successfully logged into and/or registered my username and password in the system | Story | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-18 14:27 | 2015-06-23 18:18 | 2015-06-25 14:01 | 2015-06-20 18:02 |  | FDADI Release 1 |  |  | 0 | 2 | [5 empty] | FDADI-24, FDADI-25, FDADI-72, FDADI-73 |  |  | As a user, I need to have the ability to view login dialog so I know if I have successfully logged into and/or registered my username and password in the system Acceptance Criteria: 1. User must be able to view the login page --System displays login page to the user upon accessing the URL 2. User must be able to view the following dialog on the login page "New Users: Enter a username & password and select Register. Current Users: Enter your username & password and select Login." --System displays the login message to user upon accessing the URL 3. User must be able to view the following error message when an incorrect username and password combination is entered and the Login button is selected: "Invalid Login/Password" --System displays error message upon user entering an invalid username and password combination 4. User must be able to view the following prompt if a username does not meet the criteria: "Valid characters include letters, numbers, underscore(_), and period (.)" --System displays error message upon user entering an invalid username 5. User must be able to view the following prompt if a password does meet the criteria: "Minimum of 6 characters" --System displays error message upon user entering a password that does not meet the criteria 6. User must be taken to the Medication List screen once clicking the 'Register' button - this may be considered validation of a successful login/registration --System displays the Medication List screen after clicking on the 'Register' button |  |  | 100% | 14400 | 0 | [7 empty] | 0¦i000b2:i | None |  | 3 |  |  |  | Sprint 2 | FDA Drug Interactions |  |  |  | 2015-06-20 18:02 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-22 | FDADI-20 Create Method to Insert User Credentials | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:25 |  | 2015-06-25 11:08 | 2015-06-19 20:45 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Devise a method to create the user credentials in the MongoDB so that all usernames are unique to the user. |  | 100% | 100% | 3600 | 0 | [7 empty] | 0¦i000dz: | None | [5 empty] | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-21 | FDADI-20 Create Login Page | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:23 |  | 2015-06-25 10:59 | 2015-06-19 22:52 |  | FDADI Release 1 |  |  | 0 | 1 |  |  | 0 | 7200 |  |  | FDADI-85 |  | Create a page that allows a user to register a username and password. |  | 100% | 100% | 7200 | 0 | [7 empty] | 0¦i000dr: | None | [5 empty] | Sprint 2 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-20 | As a user, I want to register my unique username and password securely so I may successfully login to the system. | Story | Done | Medium | Fixed | William Hunt | William Hunt | William Hunt | 2015-06-18 14:22 | 2015-06-23 17:12 | 2015-06-25 14:02 | 2015-06-20 18:01 |  | FDADI Release 1 |  |  | 0 | 2 | [5 empty] | FDADI-21, FDADI-22, FDADI-71 |  |  | As a user, I want to register my unique username and password securely so I may successfully login to the system. Acceptance Criteria: 1. A user must be able to view the initial login screen with the fields 'Username' and 'Password' and the buttons 'Register' and 'Login' --User is able to view the buttons and login fields 2. A user cannot submit registration without completing the mandatory fields to include 'Username' and 'Password' --User does not properly populate mandatory fields and the system will populate a message "invalid login/password" 3. Username must include valid characters such as letters, numbers, underscore(_) and period (.) --User does not enter required information in desired format and the system populates an error message 4. Password must be a minimum of 6 characters --User does not enter required information in desired format and the system populates an error message 5. User must be able to click the 'Register' button to commit username and password to the database --User clicks the 'Register' button and the system commits the information to the database 6. Information from the form must be stored in the registration database --The system stores the information supplied by the user in the registration database 7. User must be able to click the 'Login' button to access the system --User clicks the 'Login' button and the system displays the Medications List page |  |  | 100% | 10800 | 0 | [7 empty] | 0¦i000b2: | None |  | 3 |  |  |  | Sprint 2 | FDA Drug Interactions |  |  |  | 2015-06-20 18:01 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-19 | FDADI-18 Create recall alert page | Sub-task | Done | Medium | Incomplete | Timothy Scott | William Hunt | William Hunt | 2015-06-18 14:20 |  | 2015-06-25 10:58 | 2015-06-23 11:31 |  | FDADI Release 1 |  |  | 0 | 1 | [6 empty] | FDADI-88 |  | Create a page that displays an alert if a medication is recalled | [12 empty] | 0¦i000dj: | None | [5 empty] | Sprint 4 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-18 | Alert if any of the medications for a user are recalled | Story | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:18 |  | 2015-06-23 17:12 | 2015-06-23 12:29 |  |  |  |  | 0 | 1 | [5 empty] | FDADI-19, FDADI-94 | FDADI-88, FDADI-90 |  | As a user, upon login, I want to be alerted to any of my medications that are currently being recalled so that I do not use them. | [12 empty] | 0¦i000b2:yi | None |  | 2 |  |  |  | Sprint 4 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-17 | FDADI-10 Story Review | Sub-task | Done | Medium | Fixed | Srinivas Kankanahalli [Administrator] | William Hunt | William Hunt | 2015-06-18 14:13 | 2015-06-22 21:03 | 2015-06-25 11:09 | 2015-06-18 21:49 |  | FDADI Release 1 |  |  | 0 | 2 | [21 empty] | 0¦i000db: | None | 2015-06-18 21:48 |  |  |  |  | Sprint 1 |  |  |  |  | 2015-06-18 21:49 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-16 | FDADI-10 Setup MongoDB | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:13 |  | 2015-06-25 11:09 | 2015-06-18 15:11 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Setup MongoDB on an AWS instance | [12 empty] | 0¦i000d3: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-15 | FDADI-10 Setup AWS Tomcat | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:12 |  | 2015-06-25 11:08 | 2015-06-18 22:23 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Setup the AWS Tomcat instance | [12 empty] | 0¦i000cv: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-14 | FDADI-10 Setup Bamboo | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:07 |  | 2015-06-25 11:09 | 2015-06-18 15:10 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Setup Bamboo to perform continuous builds for the FDADI project | [12 empty] | 0¦i000cn: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-13 | FDADI-10 Link GitHub and JIRA | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:06 |  | 2015-06-25 11:09 | 2015-06-18 22:22 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Setup the link between the FDADI GitHub and JIRA | [12 empty] | 0¦i000cf: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-12 | FDADI-10 Create JIRA project for FDADI | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:05 |  | 2015-06-25 11:09 | 2015-06-18 15:09 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create a JIRA project for FDADI | [12 empty] | 0¦i000c7: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-11 | FDADI-10 Setup GitHub | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:04 |  | 2015-06-25 11:09 | 2015-06-18 22:22 |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | Create a new project in GitHub for the FDADI project | [12 empty] | 0¦i000bz: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-10 | Setup development infrastructure | Story | Done | High | Done | Gopal Kankanahalli | William Hunt | William Hunt | 2015-06-18 14:03 | 2015-06-29 15:05 | 2015-06-24 14:53 | 2015-06-18 22:23 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-11, FDADI-12, FDADI-13, FDADI-14, FDADI-15, FDADI-16, FDADI-17 |  |  | Setup the development infrastructure, including: JIRA, Bamboo, GitHub, AWS, and MongoDB. | [12 empty] | 0¦i000az: | None | 2015-06-18 22:23 | 3 |  |  |  | Sprint 1 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-9 | FDADI-5 Create the document | Sub-task | Done | Medium | Fixed | Gopal Kankanahalli | William Hunt | William Hunt | 2015-06-18 14:00 |  | 2015-06-25 11:08 | 2015-06-19 06:48 |  | FDADI Release 1 |  |  | 0 | 3 | [8 empty] | Create the Project Plan document using the supplied template | [12 empty] | 0¦i000br: | None | [5 empty] | Sprint 1 |  |  |  |  | 2015-06-18 15:29 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-8 | FDADI-4 Create the document | Sub-task | Done | Medium | Done | William Hunt | William Hunt | William Hunt | 2015-06-18 14:00 |  | 2015-06-25 11:08 | 2015-06-19 08:52 |  | FDADI Release 1 |  |  | 0 | 2 | [8 empty] | Create the Feature Specification document using the supplied template | [12 empty] | 0¦i000bj: | None | [5 empty] | Sprint 1 | [6 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-7 | FDADI-3 Create the document | Sub-task | Done | Medium | Done | Matt Robinson | William Hunt | William Hunt | 2015-06-18 13:56 | 2015-06-22 21:42 | 2015-06-25 16:18 | 2015-06-18 22:55 |  | FDADI Release 1 |  |  | 0 | 3 | [8 empty] | Create the Business document using the supplied template | [12 empty] | 0¦i000bb: | None | [5 empty] | Sprint 1 |  |  |  |  | 2015-06-20 11:20 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-6 | FDADI-2 Create the document | Sub-task | Done | Medium | Fixed | Gopal Kankanahalli | William Hunt | William Hunt | 2015-06-18 13:54 |  | 2015-06-25 11:08 | 2015-06-19 06:49 |  | FDADI Release 1 |  |  | 0 | 3 | [8 empty] | Create the document using the supplied template. | [12 empty] | 0¦i000b3: | None | [5 empty] | Sprint 1 |  |  |  |  | 2015-06-18 15:28 |  | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-5 | Create Project Plan Document | Story | Done | Medium | Fixed | Ms. Divya Sharma | William Hunt | William Hunt | 2015-06-18 13:47 | 2015-06-22 19:16 | 2015-06-24 15:40 | 2015-06-19 06:49 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-9 | [15 empty] | 0¦i000al: | None |  | 5 |  |  |  | Sprint 1 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-4 | Create Feature Specification Document | Story | Done | Medium | Done | Ms. Divya Sharma | William Hunt | William Hunt | 2015-06-18 13:46 |  | 2015-06-24 15:40 | 2015-06-19 08:52 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-8 | [15 empty] | 0¦i000b0:i | None |  | 5 |  |  |  | Sprint 1 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-3 | Create Business Document | Story | Done | Highest | Done | Ms. Divya Sharma | William Hunt | William Hunt | 2015-06-18 13:46 | 2015-06-22 21:42 | 2015-06-24 14:53 | 2015-06-18 22:56 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-7 |  |  | As a system architect, I need to create the Business (EPIC) document for use by the developers and testers. | [12 empty] | 0¦i000b0: | None |  | 5 |  |  |  | Sprint 1 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-2 | As a system architect, I need to create the Technical Design (Technical Approach) document so that the developers and testers can complete their tasks. | Story | Done | Highest | Fixed | Ms. Divya Sharma | William Hunt | William Hunt | 2015-06-18 13:32 | 2015-06-22 19:22 | 2015-06-24 14:53 | 2015-06-19 06:49 |  | FDADI Release 1 |  |  | 0 | 1 | [5 empty] | FDADI-6 |  |  | As a system architect, I need to create the Technical Design (Technical Approach) document so that the developers and testers can complete their tasks. Acceptance Criteria: 1. System Architect creates document 2. Document is reviewed by team and Product Owner 3. Document is uploaded to the share repository | [12 empty] | 0¦i000b0:r | None |  | 5 |  |  |  | Sprint 1 | FDA Drug Interactions | [5 empty] | None |  |  |  | Not Started |  |  | None
FDA Drug Interactions | FDADI-1 | As a user, I want to research medication and be alerted through a prompt to add or reject any drug that has a recall or carries interactions between my existing medications. | Epic | Open | Medium | Unresolved | Unassigned | William Hunt | William Hunt | 2015-06-18 13:28 | 2015-06-28 17:30 | 2015-06-25 13:41 |  |  | FDADI Release 1 |  |  | 0 | 1 | [8 empty] | As a user, on my desktop as well as my mobile devices, I want to login in and compile a list of my medications and be alerted to any recalls, adverse reactions, and any drug interactions between my medications so that I stay healthy. | [7 empty] | FDA Drug Interactions |  |  | To Do | ghx-label-1 | 0¦i0009z: | None | [12 empty] | None |  |  |  | Not Started |  |  | None
Generated at Mon Jul 06 11:27:43 EDT 2015 by Ms. Nelofur Damiani using JIRA 6.5-OD-08-001#65007-sha1:1fc98468dfd18a5f35861f5c2ab67219b6b6f2f6.